## RFB
Request for Bids
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Prequalification (Y/N) | Procurement Process | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Pre-qualification Documents |  | Specific Procurement Notice |  | Amendments to Pre-qualification Documents | Opening / Minutes of Pre-qualification |  | Pre-qualification Evaluation Report |  | Draft Bidding Documents |  | Specific Procurement Notice |  | Invitation to Providers |  | Amendments to Bidding Documents | Bid Submission / Opening / Minutes |  | Bid Evaluation Report and Recommendation for Award |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[15 empty] | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BF-WURI - BURKINA FASO-343445-GO-RFB / Acquisition d’un serveur physiques au profit de l’ANPTIC | No | IDA-D6090 | Establishing Robust and Inclusive fID Systems | Post | Goods | Open - National | N | Single Stage One Envelope |  | 959439 |  | Request for Bids SPD (Goods) - 1 envelope process | Pending Implementation | Autorisé | [9 empty] | 2023/04/28 |  | 2023/05/03 |  |  |  |  | 2023/06/02 |  | 2023/06/23 |  | 2023/07/07 |  | 2023/07/28 |  |  | 2023/09/26

## RFQ
Request for Quotations
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Request for Quotations |  | Specific Procurement Notice |  | Invitation to Supplier / Contractor |  | Amendments to Request for Quotations | Receive Quotations |  | Comparison of Quotations |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BF-WURI - BURKINA FASO-354612-NC-RFQ / Recrutement d'un prestataire pour la fourniture de pause café et pause déjeuner au profit du Projet WURI | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Non-consulting Services | Limited | 24712 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Not Submitted | Renvoyé | 2023/04/28 | [6 empty] | 2023/05/09 |  | 2023/05/10 |  | 2023/05/24 |  | 2023/06/14 |  |  | 2024/06/08
BF-WURI - BURKINA FASO-349745-GO-RFQ / Acquisition d'équipements de transports (2 véhicules station wagon + 1 véhicule 4x 4 pick-up au profit de l’UGP du projet WURI | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 210873 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/04/28 | [6 empty] | 2023/05/09 |  | 2023/05/10 |  | 2023/05/24 |  | 2023/06/14 |  |  | 2023/09/12
BF-WURI - BURKINA FASO-342120-GO-RFQ / Acquisition de matériels et équipements de bureau au profit de l'UGP du projet WURI (matériels informatiques périinformatiques, système de vidéo surveillance, de sécurité, matériels de communication, extincteurs, matériels divers | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 82372 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/04/28 | [6 empty] | 2023/05/09 |  | 2023/05/10 |  | 2023/05/24 |  | 2023/06/14 |  |  | 2023/07/29
BF-WURI - BURKINA FASO-279918-GO-RFQ / Acquisition de matériels informatiques pour la dématérialisation de la procédure de réception et de traitement des plaintes au profit de la CIL | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 24712 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Under Implementation | Autorisé | 2022/05/10 | 2022/09/27 | [5 empty] | 2022/05/21 | 2022/10/03 | 2022/05/22 | 2022/10/03 | 2022/06/02 | 2022/11/11 | 2022/06/16 |  |  | 2022/07/31
BF-WURI - BURKINA FASO-257407-NC-RFQ / Acquisition du matériel électroménager | No | IDA-66100 | Strengthening the Legal and Institutional Framework | Post | Non-consulting Services | Limited | 16474 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Autorisé | 2021/10/18 | 2021/11/24 | [5 empty] | 2021/11/06 | 2021/12/02 | 2021/11/13 | 2021/12/02 | 2021/11/27 | 2021/12/07 | 2021/12/18 | 2022/01/18 |  | 2022/01/17 | 2022/04/29
BF-WURI - BURKINA FASO-309525-GO-RFQ / Acquisition d'un véhicule 4x4 station Wagon et d'une motocyclette | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 75782 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Autorisé | 2022/08/30 | 2022/09/01 | [5 empty] | 2022/09/07 | 2022/09/07 | 2022/09/08 | 2022/09/07 | 2022/09/11 | 2022/11/11 | 2022/09/25 |  |  | 2022/12/24
BF-WURI - BURKINA FASO-309540-GO-RFQ / Acquisition de panneaux indication du projet au profit de l’UGP | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 4119 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Autorisé | 2022/08/30 | 2022/09/09 | [5 empty] | 2022/09/07 | 2022/09/19 | 2022/09/08 | 2022/09/19 | 2022/09/11 | 2022/11/11 | 2022/09/25 |  |  | 2022/10/25
BF-WURI - BURKINA FASO-257405-NC-RFQ / Fourniture d'internet au profit de l'UGP | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Non-consulting Services | Limited | 16474 |  | Request for Quotations (Non Bank-SPD) | Canceled | Autorisé | 2021/10/18 | [6 empty] | 2021/11/06 |  | 2021/11/13 |  | 2021/11/27 |  | 2021/12/18 |  |  | 2022/02/16
BF-WURI - BURKINA FASO-257402-CW-RFQ / Réalisation du cloisonnement et du câblage électrique des locaux de l’UGP | No | IDA-66100 | Establishing Robust and Inclusive fID Systems | Post | Works | Limited | 8237 |  | Request for Quotations - Small Works (Emergency) SPD -Competitive | Canceled | Autorisé | 2021/10/18 | 2021/11/28 | [5 empty] | 2021/11/06 |  | 2021/11/13 |  | 2021/11/27 |  | 2021/12/18 |  |  | 2022/01/17
BF-WURI - BURKINA FASO-257400-NC-RFQ / Gardiennage des locaux | No | IDA-66100 | Establishing Robust and Inclusive fID Systems | Post | Non-consulting Services | Limited | 3295 |  | Request for Quotations (Non Bank-SPD) | Signed | Autorisé | 2021/10/18 | 2022/03/08 | [5 empty] | 2021/11/06 | 2022/03/02 | 2021/11/13 | 2022/03/02 | 2021/11/27 | 2022/04/11 | 2021/12/18 | 2022/03/28 |  | 2022/12/18
BF-WURI - BURKINA FASO-204355-GO-RFQ / Acquisition de fournitures de bureau au profit de l'UGP | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Goods | Limited | 10708 |  | Request for Quotations (Non Bank-SPD) | Completed | Autorisé | 2021/10/18 | 2021/11/24 | [5 empty] | 2021/11/06 | 2021/12/01 | 2021/11/13 | 2021/12/01 | 2021/11/27 | 2021/12/07 | 2021/12/18 | 2022/01/18 |  | 2022/02/16 | 2022/04/29
BF-WURI - BURKINA FASO-342126-NC-RFQ / Recrutement d'un prestataire pour assurer le gardiennage des locaux du projet WURI | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Non-consulting Services | Limited | 10873 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/04/20 | [6 empty] | 2023/05/01 |  | 2023/05/02 |  | 2023/05/16 |  | 2023/06/06 |  |  | 2024/05/31
BF-WURI - BURKINA FASO-309532-GO-RFQ / Acquisition d’un système complet de vidéo conférence au profit de l'UGP/WURI | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 29160 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Autorisé | 2022/08/30 | 2022/11/23 | [5 empty] | 2022/09/07 | 2022/09/21 | 2022/09/08 | 2022/09/21 | 2022/09/11 | 2022/11/11 | 2022/09/25 |  |  | 2022/11/24
BF-WURI - BURKINA FASO-299969-GO-RFQ / Acquisition de matériel informatique et péri informatique au profit de l'UGP | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 28896 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Autorisé | 2022/06/22 | 2022/05/13 | [5 empty] | 2022/07/04 | 2022/05/20 | 2022/07/05 | 2022/05/20 | 2022/07/15 | 2022/06/02 | 2022/08/08 | 2022/08/05 |  | 2022/09/07 | 2022/10/13
BF-WURI - BURKINA FASO-204349-GO-DIR / Acquisition de deux (2) véhicules à 4 roues et d'une motocyclette au profit de l'UGP | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Goods | Limited | 72000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Autorisé | 2021/10/20 | 2022/03/26 | [5 empty] | 2021/11/04 | 2022/03/18 | 2021/11/11 | 2022/03/18 | 2021/11/25 | 2022/04/10 | 2021/12/16 | 2022/05/03 |  | 2022/06/14 | 2022/08/04
BF-WURI - BURKINA FASO-204353-GO-RFQ / Acquisition de matériel informatiques au profit de l'UGP | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Goods | Limited | 26359 |  | Request for Quotations (Non Bank-SPD) | Terminated | Autorisé | 2021/10/18 | 2021/11/25 | [5 empty] | 2021/11/06 | 2021/11/25 | 2021/11/13 | 2021/11/29 | 2021/11/27 | 2021/12/01 | 2021/12/18 | 2022/01/10 |  | 2022/02/16 |  | 2022/04/07
BF-WURI - BURKINA FASO-204354-GO-RFQ / Acquisition de mobilier de bureau au profit de l'UGP | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Goods | Limited | 43305 |  | Request for Quotations (Non Bank-SPD) | Terminated | Autorisé | 2021/10/18 | 2021/11/24 | [5 empty] | 2021/11/06 | 2021/12/02 | 2021/11/13 | 2021/12/02 | 2021/11/27 | 2021/12/07 | 2021/12/18 | 2022/01/18 |  | 2022/02/16 |  | 2022/05/13
BF-WURI - BURKINA FASO-342105-NC-RFQ / Souscription à une assurance maladie au profit du personnel de l'UGP | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Non-consulting Services | Limited | 26359 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/04/20 | [6 empty] | 2023/05/01 |  | 2023/05/02 |  | 2023/05/16 |  | 2023/06/06 |  |  | 2024/05/31
BF-WURI - BURKINA FASO-257403-CW-RFQ / Réalisation du câblage informatique des locaux de l’UGP | No | IDA-66100 | Establishing Robust and Inclusive fID Systems | Post | Works | Limited | 19769 |  | Request for Quotations - Small Works (Emergency) SPD -Competitive | Signed | Autorisé | 2021/10/18 | 2022/08/22 | [5 empty] | 2021/11/06 | 2022/08/29 | 2021/11/13 | 2022/08/29 | 2021/11/27 | 2022/10/25 | 2021/12/18 |  |  | 2022/01/17
BF-WURI - BURKINA FASO-299966-GO-RFQ / Acquisition de mobilier de bureau au profit de l'UGP | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 45295 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Autorisé | 2022/06/22 | 2022/07/21 | [5 empty] | 2022/07/03 | 2022/07/27 | 2022/07/04 | 2022/07/27 | 2022/07/15 | 2022/08/01 | 2022/08/09 | 2022/08/12 |  | 2022/09/08 | 2022/09/16
BF-WURI - BURKINA FASO-257399-NC-RFQ / Entretien et nettoyage des locaux | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Non-consulting Services | Limited | 3295 |  | Request for Quotations (Non Bank-SPD) | Signed | Autorisé | 2021/10/18 | 2022/03/08 | [5 empty] | 2021/11/06 | 2022/03/02 | 2021/11/13 | 2022/03/02 | 2021/11/27 | 2022/03/11 | 2021/12/18 | 2022/03/28 |  | 2022/12/18
BF-WURI - BURKINA FASO-342128-NC-RFQ / Recrutement des prestataires pour assurer l'entretien, la maintenance et la réparation de matériels de transport, matériels et mobilier de bureau | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Non-consulting Services | Limited | 16474 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/06/30 | [6 empty] | 2023/07/11 |  | 2023/07/12 |  | 2023/07/26 |  | 2023/08/16 |  |  | 2024/08/10
BF-WURI - BURKINA FASO-309534-GO-RFQ / Acquisition et installation d’un autocommutateur et de postes téléphoniques | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 7001 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Autorisé | 2022/08/30 | 2022/09/01 | [5 empty] | 2022/09/07 | 2022/09/08 | 2022/09/08 | 2022/09/08 | 2022/09/11 | 2022/11/04 | 2022/09/25 |  |  | 2022/10/25
BF-WURI - BURKINA FASO-279917-GO-RFQ / Acquisition de matériel informatique et périinformatique au profit de l'UGP | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 56013 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Autorisé | 2022/03/15 | 2022/05/13 | [5 empty] | 2022/03/26 | 2022/05/20 | 2022/03/27 | 2022/05/20 | 2022/04/07 | 2022/06/02 | 2022/04/21 | 2022/07/07 |  | 2022/06/20 | 2022/10/13
BF-WURI - BURKINA FASO-279911-NC-RFQ / Entretien et réparation de véhicules | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Non-consulting Services | Limited | 3295 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2022/07/15 | [6 empty] | 2022/07/26 |  | 2022/07/27 |  | 2022/08/07 |  | 2022/08/21 |  |  | 2023/08/21
BF-WURI - BURKINA FASO-342118-GO-RFQ / Acquisition des fournitures de bureau et consommables informatiques u profit du projet WURI | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 24712 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/04/30 | [6 empty] | 2023/05/11 |  | 2023/05/12 |  | 2023/05/26 |  | 2023/06/16 |  |  | 2023/07/16
BF-WURI - BURKINA FASO-342108-GO-RFQ / Acquisition de mobiliers de bureau au profit de l'UGP | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 24712 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/04/28 | [6 empty] | 2023/05/09 |  | 2023/05/10 |  | 2023/05/24 |  | 2023/06/14 |  |  | 2023/07/14
BF-WURI - BURKINA FASO-280274-GO-RFQ / Acquisition de consommables informatiques et produits d'entretien | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 8237 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Autorisé | 2022/04/11 | 2022/09/23 | [5 empty] | 2022/04/22 | 2022/09/30 | 2022/04/23 | 2022/09/23 | 2022/05/04 | 2022/11/11 | 2022/05/18 |  |  | 2023/05/18
BF-WURI - BURKINA FASO-279914-GO-RFQ / Acquisition et installation d'un groupe électrogène de 200 KVA avec grille de protection au profit de l’UGP | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 32949 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Autorisé | 2022/03/01 | 2022/08/23 | [5 empty] | 2022/03/12 | 2022/08/31 | 2022/03/13 | 2022/08/31 | 2022/03/24 | 2022/10/26 | 2022/04/07 |  |  | 2022/08/05
BF-WURI - BURKINA FASO-257373-GO-RFQ / Acquisition de logiciel de gestion comptable et financière (TomPro) au profit de l'UGP | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Goods | Open - National | 81549 |  | Request for Quotations - Goods (Emergency) SPD - Competitive | Signed | Autorisé | 2021/10/18 | 2021/12/06 | 2021/10/23 |  | 2021/10/23 | 2021/12/09 |  | 2021/11/06 | 2021/12/09 | 2021/11/13 | 2021/12/09 | 2021/11/27 | 2021/12/13 | 2021/12/18 | 2022/01/10 |  | 2022/01/17
BF-WURI - BURKINA FASO-349747-GO-RFQ / Acquisition d’équipement complémentaire (ordinateurs, imprimantes, appareils photos booth) pour la réalisation de l'enrôlement pilote | No | IDA-D6090 | Establishing Robust and Inclusive fID Systems | Post | Goods | Limited | 26359 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/04/20 | [6 empty] | 2023/05/01 |  | 2023/05/02 |  | 2023/05/16 |  | 2023/06/06 |  |  | 2023/07/06
BF-WURI - BURKINA FASO-342122-GO-RFQ / Acquisition d'un logiciel de gestion de la paie (TomPaie) | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 12356 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/04/28 | [6 empty] | 2023/05/09 |  | 2023/05/10 |  | 2023/05/24 |  | 2023/06/14 |  |  | 2023/07/14
BF-WURI - BURKINA FASO-309542-CW-RFQ / Travaux de cloisonnement des bureaux du projet | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Works | Limited | 12356 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Autorisé | 2022/08/30 | 2022/09/07 | [5 empty] | 2022/09/07 | 2022/09/13 | 2022/09/08 | 2022/09/13 | 2022/09/11 | 2022/11/11 | 2022/09/25 |  |  | 2022/10/25
BF-WURI - BURKINA FASO-279916-GO-RFQ / Acquisition et installation de climatiseurs au profit de l’UGP | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Limited | 8237 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Canceled | Autorisé | 2022/03/30 | [6 empty] | 2022/04/10 |  | 2022/04/11 |  | 2022/04/22 |  | 2022/05/06 |  |  | 2022/06/05

## DIR
Direct Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Procurement Category | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Justification for Direct Procurement |  | Invitation to Supplier / Contractor |  | Draft Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BF-WURI - BURKINA FASO-342127-NC-DIR / Recrutement d'un prestataire pour le nettoyage des locaux de l'UGP | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Non-consulting Services | Direct - National | 13180 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/04/17 |  | 2023/04/18 |  | 2023/04/28 |  | 2023/05/05 |  | 2023/05/26 |  |  | 2024/05/20
BF-WURI - BURKINA FASO-257397-NC-DIR / Location des locaux de l'UGP | No | IDA-66100 | Establishing Robust and Inclusive fID Systems | Post | Non-consulting Services | Direct | 4942 |  | Other (with field for explanation) | Canceled | Autorisé | 2021/10/08 |  | 2021/10/09 |  | 2021/10/10 |  | 2021/10/11 |  | 2021/10/15 |  |  | 2022/04/13
BF-WURI - BURKINA FASO-257396-GO-DIR / Acquisition de carburant et lubrifiants | No | IDA-66100 | Establishing Robust and Inclusive fID Systems | Post | Goods | Direct | 3295 |  | Other (with field for explanation) | Completed | Autorisé | 2021/10/18 | 2022/06/07 | 2021/10/23 | 2022/04/15 | 2021/10/23 | 2022/04/15 | 2021/11/06 | 2022/04/29 | 2021/11/27 | 2022/05/17 |  | 2021/11/30 | 2022/06/16
BF-WURI - BURKINA FASO-257401-NC-DIR / Souscription à une assurance maladie au profit du personnel de l'UGP | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Non-consulting Services | Direct | 24712 |  | Other (with field for explanation) | Completed | Autorisé | 2021/10/18 | 2022/03/12 | 2021/10/23 | 2022/01/10 | 2021/10/23 | 2022/03/12 | 2021/11/06 | 2022/01/24 | 2021/11/27 | 2022/03/10 |  | 2022/11/27 | 2023/03/21
BF-WURI - BURKINA FASO-342123-GO-DIR / Acquisition de carburant et lubrifiants au profit de l'UGP/WURI | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Goods | Direct - National | 16474 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Autorisé | 2023/04/28 |  | 2023/04/29 |  | 2023/05/09 |  | 2023/05/16 |  | 2023/06/06 |  |  | 2024/05/31

## QCBS - FBS - LCS
Quality and Cost Based Selection (QCBS), Fixed Budget Based Selection (FBBS), Least Cost Based Selection (LCBS)
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Request for Proposals as Issued |  | Amendments to Request for Proposals |  | Opening of Technical Proposals / Minutes |  | Evaluation of Technical Proposals |  | Opening of Financial Proposals / Minutes |  | Combined Evaluation Report and Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BF-WURI - BURKINA FASO-204340-CS-QCBS / Réaliser un audit financier et comptable externe | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open - National | 11532 | Signed | Autorisé | 2021/10/18 | 2021/11/26 | 2021/10/18 | 2022/02/11 | 2021/11/01 | 2022/03/25 | 2021/11/01 | 2022/04/15 |  |  | 2021/11/01 |  | 2021/11/29 | 2022/05/16 | 2021/12/29 | 2022/05/25 | 2022/01/12 | 2022/06/13 | 2022/02/02 | 2022/06/13 | 2022/02/16 | 2022/11/21 | 2022/03/09 |  |  | 2022/04/08
BF-WURI - BURKINA FASO-279907-CS-QCBS / Recrutement d'un cabinet pour la mise en place du système fID | No | IDA-D6090 | Establishing Robust and Inclusive fID Systems | Prior | Consultant Services | Open - International | 1515651 | Pending Implementation | Autorisé | 2022/06/20 |  | 2022/07/05 |  | 2022/07/12 |  | 2022/08/11 |  |  |  | 2022/08/11 |  | 2022/08/12 |  | 2022/08/19 |  | 2022/08/26 |  | 2022/09/09 |  | 2022/09/16 |  | 2022/10/07 |  |  | 2023/10/07
BF-WURI - BURKINA FASO-282943-CS-QCBS / Sélection d’un cabinet pour le suivi contrôle technique de la mise en place des systèmes applicatifs du fID | No | IDA-D6090 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open - International | 500000 | Under Implementation | Autorisé | 2022/03/30 | 2022/04/15 | 2022/04/14 | 2022/05/04 | 2022/04/21 | 2022/06/01 | 2022/05/21 | 2022/07/26 |  |  | 2022/05/21 |  | 2022/05/22 | 2022/08/30 | 2022/05/29 | 2022/09/12 | 2022/06/05 | 2022/12/09 | 2022/06/19 | 2023/01/25 | 2022/06/30 |  | 2022/07/21 |  |  | 2023/07/21

## CQS
Consultant Qualification
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BF-WURI - BURKINA FASO-204338-CS-QCBS / Sélection d’un Cabinet juridique pour le cadre législatif et réglementaire du système | No | IDA-66100 | Strengthening the Legal and Institutional Framework | Post | Consultant Services | Open - International | 247117 | Signed | Autorisé | 2021/10/16 | 2021/11/05 | 2021/10/18 | 2022/01/20 | 2021/12/06 | 2022/02/15 | 2021/12/20 | 2022/04/06 | 2022/01/19 | 2022/04/08 | 2022/02/02 | 2022/05/10 | 2022/02/23 | 2022/05/13 |  | 2022/08/22
BF-WURI - BURKINA FASO-282947-CS-CQS / Analyse de l’écosystème infrastructurel informatique du Burkina Faso pour la mise en place de l’infrastructure (serveurs et database) du système de fID | No | IDA-D6090 | Establishing Robust and Inclusive fID Systems | Post | Consultant Services | Open - International | 65898 | Canceled | Autorisé | 2022/03/30 |  | 2022/04/14 |  | 2022/04/29 |  | 2022/05/06 |  | 2022/05/09 |  | 2022/05/20 |  | 2022/06/03 |  |  | 2022/11/30
BF-WURI - BURKINA FASO-279910-CS-CQS / Recrutement d'un cabinet pour la traduction de la loi N°001-2021/AN en trois langues nationales | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Consultant Services | Limited | 13180 | Signed | Autorisé | 2022/07/15 | 2022/10/19 |  |  |  |  | 2022/07/22 | 2022/11/16 | 2022/08/05 | 2022/12/13 | 2022/08/16 | 2023/01/11 | 2022/09/06 |  |  | 2022/11/05
BF-WURI - BURKINA FASO-204336-CS-QCBS / Elaboration d'une stratégie de communication | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open - National | 49423 | Signed | Autorisé | 2021/10/16 | 2022/05/28 | 2021/10/18 | 2022/07/20 | 2021/11/17 | 2022/08/12 | 2021/12/01 | 2022/08/12 | 2021/12/31 | 2022/09/15 | 2022/01/14 | 2022/09/29 | 2022/02/04 |  |  | 2022/08/03
BF-WURI - BURKINA FASO-309551-CS-CQS / Recruter un cabinet de juriste pour élaborer le projet de loi d’orientation sur le numérique | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Consultant Services | Open - International | 164745 | Under Review | Autorisé | 2022/08/30 | 2022/12/23 | 2022/09/13 |  | 2022/09/20 |  | 2022/09/25 |  | 2022/10/25 |  | 2022/11/08 |  | 2022/11/29 |  |  | 2023/02/27
BF-WURI - BURKINA FASO-342130-CS-CQS / Recrutement d'un cabinet de consultant chargé de l'élaboration d'une stratégie d'intégration de l'état civil au système d'identification de base du Burkina Faso assortie d'un plan d'action | No | IDA-D6090 | Establishing Robust and Inclusive fID Systems | Post | Consultant Services | Open - National | 82372 | Pending Implementation | Autorisé | 2023/06/30 |  | 2023/07/15 |  | 2023/07/22 |  | 2023/07/29 |  | 2023/08/28 |  | 2023/09/11 |  | 2023/10/02 |  |  | 2023/12/31
BF-WURI - BURKINA FASO-279382-CS-CQS / Sélection d’un cabinet pour la conception d’une plateforme de réception et de traitement des plaintes au profit de la CIL | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Consultant Services | Open - National | 57661 | Pending Implementation | Autorisé | 2022/03/10 |  | 2022/03/25 |  | 2022/04/09 |  | 2022/04/16 |  | 2022/04/19 |  | 2022/04/30 |  | 2022/05/14 |  |  | 2022/08/12
BF-WURI - BURKINA FASO-257417-CS-CQS / Recrutement d'un cabinet RH pour recruter le personnel d'appui à l'UGP | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open - International | 65898 | Canceled | Autorisé | 2021/10/08 | 2021/11/09 | 2021/10/18 |  | 2021/11/01 |  | 2021/11/01 |  | 2021/11/01 |  | 2021/11/04 |  | 2021/11/09 |  |  | 2022/01/08
BF-WURI - BURKINA FASO-279395-CS-CQS / Recrutement d'un cabinet pour l'élaboration d'une stratégie de numérisation de l'état civil | No | IDA-D6090 | Establishing Robust and Inclusive fID Systems | Post | Consultant Services | Open - National | 82372 | Pending Implementation | Autorisé | 2022/04/14 |  | 2022/04/29 |  | 2022/05/14 |  | 2022/05/21 |  | 2022/05/24 |  | 2022/06/04 |  | 2022/06/18 |  |  | 2022/09/16
BF-WURI - BURKINA FASO-279405-CS-CQS / Recrutement d’un cabinet RH pour appuyer le recrutement du personnel | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Consultant Services | Limited | 65898 | Signed | Autorisé | 2022/03/10 | 2022/03/02 |  |  |  |  | 2022/03/17 | 2022/02/10 | 2022/04/01 | 2022/03/18 | 2022/04/12 | 2022/03/22 | 2022/04/26 | 2022/04/06 |  | 2022/06/25
BF-WURI - BURKINA FASO-257406-CS-CQS / Elaboration d'un manuel de gestion des plaintes | No | IDA-66100 | Strengthening the Legal and Institutional Framework | Post | Consultant Services | Limited | 57661 | Canceled | Autorisé | 2021/10/18 | 2021/10/26 |  |  |  |  | 2021/11/01 |  | 2021/12/01 |  | 2021/12/15 |  | 2022/01/05 |  |  | 2022/03/06
BF-WURI - BURKINA FASO-204329-CS-QCBS / Elaboration d'une stratégie d'interopérabilité du système fID et des systèmes sectoriels | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open - National | 82372 | Signed | Autorisé | 2021/10/16 | 2022/03/29 | 2021/10/18 | 2022/04/07 | 2021/11/17 | 2022/05/12 | 2021/12/01 | 2022/05/12 | 2021/12/31 | 2022/06/20 | 2022/01/14 | 2022/07/29 | 2022/02/04 | 2022/08/18 |  | 2022/08/03
BF-WURI - BURKINA FASO-257404-CS-QCBS / Réalisation d’un site web et de la charte graphique du projet | No | IDA-66110 | Establishing Robust and Inclusive fID Systems | Post | Consultant Services | Open - National | 16474 | Signed | Autorisé | 2021/10/16 | 2021/10/26 | 2021/10/18 | 2022/01/16 | 2021/11/17 | 2022/02/14 | 2021/12/01 | 2022/03/26 | 2021/12/31 | 2022/03/15 | 2022/01/14 | 2022/04/29 | 2022/02/04 | 2022/05/03 |  | 2022/03/06

## INDV
Individual Consultant Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Justification for Direct Selection |  | Invitation to Identified / Selected Consultant |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BF-WURI - BURKINA FASO-204367-CS-CQS / Recrutement d'un Assistant en gestion de plaintes | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open | 40000 | Canceled | Autorisé | 2021/11/29 |  | 2021/12/13 |  | 2022/01/12 |  |  |  | 2022/01/17 |  | 2022/02/07 |  | 2022/02/21 |  | 2022/03/14 |  |  | 2023/03/14
BF-WURI - BURKINA FASO-204343-CS-CQS / Recrutement d'un Comptable | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open | 40000 | Canceled | Autorisé | 2021/10/08 |  | 2021/10/23 |  | 2021/10/24 |  |  |  | 2021/10/25 |  | 2021/10/26 |  | 2021/10/27 |  | 2021/11/01 |  |  | 2022/11/01
BF-WURI - BURKINA FASO-280014-CS-INDV / Élaboration d'un manuel de gestion des plaintes | No | IDA-D6090 | Strengthening the Legal and Institutional Framework | Post | Consultant Services | Limited | 57661 | Signed | Autorisé | 2022/03/10 | 2022/03/02 | [6 empty] | 2022/03/15 | 2022/03/09 | 2022/03/29 | 2022/08/10 | 2022/04/12 | 2022/08/10 | 2022/05/03 | 2022/09/08 |  | 2022/07/02
BF-WURI - BURKINA FASO-204364-CS-CQS / Recrutement d'un architecte technique | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open | 40000 | Canceled | Autorisé | 2021/11/29 |  | 2021/12/13 |  | 2022/01/12 |  |  |  | 2022/01/17 |  | 2022/02/07 |  | 2022/02/21 |  | 2022/03/14 |  |  | 2023/03/14
BF-WURI - BURKINA FASO-204379-CS-CQS / Recrutement d'un consultant pour la réalisation d'une évaluation sociale | No | IDA-66100 | Establishing Robust and Inclusive fID Systems | Post | Consultant Services | Open | 63427 | Canceled | Autorisé | 2021/10/12 |  | 2021/10/18 |  | 2021/11/17 |  |  |  | 2021/11/20 |  | 2021/12/04 |  | 2021/12/18 |  | 2022/01/08 |  |  | 2022/04/08
BF-WURI - BURKINA FASO-204366-CS-CQS / Recrutement d'un auditeur interne | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open | 40000 | Canceled | Autorisé | 2021/11/29 |  | 2021/12/13 |  | 2021/12/13 |  |  |  | 2021/12/18 |  | 2022/01/08 |  | 2022/01/22 |  | 2022/02/12 |  |  | 2023/02/12
BF-WURI - BURKINA FASO-257410-CS-INDV / Elaboration d'un manuel de suivi-évaluation | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Limited | 32949 | Signed | Autorisé | 2021/10/18 | 2021/10/26 | [6 empty] | 2021/10/23 | 2022/03/14 | 2021/11/13 | 2022/01/17 | 2021/11/27 | 2022/02/03 | 2021/12/18 | 2022/05/13 |  | 2022/02/16
BF-WURI - BURKINA FASO-204345-CS-CQS / Recrutement d'un Spécialiste en suivi et évaluation | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open | 40000 | Canceled | Autorisé | 2021/11/29 |  | 2021/12/13 |  | 2022/01/12 |  |  |  | 2022/01/17 |  | 2022/02/07 |  | 2022/02/21 |  | 2022/03/14 |  |  | 2023/03/14
BF-WURI - BURKINA FASO-201038-CS-INDV / Consultant pour la réalisation d'une évaluation sociale | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open | 70000 | Signed | Autorisé | 2021/04/23 | 2022/04/29 | 2021/05/07 | 2022/06/21 | 2021/06/06 | 2020/06/03 |  |  | 2021/06/11 | 2020/07/06 | 2021/07/02 | 2020/08/03 | 2021/07/16 | 2020/09/16 | 2021/08/06 | 2020/11/18 |  | 2021/11/04
BF-WURI - BURKINA FASO-204361-CS-CQS / Elaboration d'un manuel de procédures administratives et comptables (Rédaction du manuel des opérations) | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Limited | 32949 | Canceled | Autorisé | 2021/10/18 | [7 empty] | 2021/10/23 |  | 2021/11/13 |  | 2021/11/27 |  | 2021/12/18 |  |  | 2022/06/16
BF-WURI - BURKINA FASO-257380-CS-INDV / Recrutement d'un spécialiste en gestion financière | No | IDA-66100 | Establishing Robust and Inclusive fID Systems | Post | Consultant Services | Open | 40000 | Canceled | Autorisé | 2021/10/16 |  | 2021/10/18 |  | 2021/11/17 |  |  |  | 2021/11/22 |  | 2021/12/13 |  | 2021/12/27 |  | 2022/01/17 |  |  | 2023/01/17
BF-WURI - BURKINA FASO-257393-CS-INDV / Recrutement spécialiste environnemental et social | No | IDA-66100 | Facilitating Access to Services Through fID Credentials | Post | Consultant Services | Open | 40000 | Canceled | Autorisé | 2021/11/29 |  | 2021/12/13 |  | 2022/01/12 |  |  |  | 2022/01/17 |  | 2022/02/07 |  | 2022/02/21 |  | 2022/03/14 |  |  | 2023/03/14
BF-WURI - BURKINA FASO-257395-CS-INDV / Recrutement spécialiste en communication | No | IDA-66100 | Establishing Robust and Inclusive fID Systems | Post | Consultant Services | Open | 40000 | Canceled | Autorisé | 2021/11/29 |  | 2021/12/13 |  | 2022/01/12 |  |  |  | 2022/01/17 |  | 2022/02/07 |  | 2022/02/21 |  | 2022/03/14 |  |  | 2023/03/14